## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | ACG Integrated Process Evaluation Project Plan | 58.5 days? | July 6, 2021 8:00 AM | September 24, 2021 12:00 PM |  | 0
1 | Yes | Auto Scheduled | Phase 0 | 4.96 days? | July 6, 2021 8:00 AM | July 12, 2021 4:40 PM |  | 1
2 | Yes | Auto Scheduled | Pre-Guideline Development : Set up Operational Framework and an Integrated Process for Developing Narrative & Computable Guidelines | 2.13 days? | July 6, 2021 8:00 AM | July 8, 2021 9:00 AM |  | 2
3 | Yes | Auto Scheduled | Identify functional and operational (including informatics and IT) needs and requirements and limitations for developing narrative and computable guidelines in the organization. | 0.13 days? | July 6, 2021 8:00 AM | July 6, 2021 9:00 AM |  | 3
4 | Yes | Auto Scheduled | Assess current resources and capacity for guideline development in the organization | 1 day? | July 6, 2021 9:00 AM | July 7, 2021 9:00 AM | 3 | 3
5 | Yes | Auto Scheduled | Develop an organizational framework for developing a narrative or computable guideline | 1 day? | July 7, 2021 9:00 AM | July 8, 2021 9:00 AM | 4 | 3
6 | Yes | Auto Scheduled | Phase 1 : Define Clinical Problem /Assess Clinical Need / Select Topic | 2.83 days? | July 8, 2021 9:00 AM | July 12, 2021 4:40 PM | 2 | 2
7 | Yes | Auto Scheduled | Identify and assess clinical need to identify guideline topic(s) and define clinical questions for a new or updated guideline. | 1 day? | July 8, 2021 9:00 AM | July 9, 2021 9:00 AM |  | 3
8 | Yes | Auto Scheduled | Prioritize topic(s) (if there are more than one proposed topics). | 0.5 days? | July 9, 2021 9:00 AM | July 9, 2021 2:00 PM | 7 | 3
9 | Yes | Auto Scheduled | Assess topic and research questions (guideline objective), and communication, informatics, implementation, and evaluation needs. Decide whether to produce a computable version of guideline. | 0.33 days? | July 9, 2021 2:00 PM | July 9, 2021 4:40 PM | 8 | 3 | .
10 | Yes | Auto Scheduled | Obtain leadership approval of topic and funding | 1 day? | July 9, 2021 4:40 PM | July 12, 2021 4:40 PM | 9 | 3
11 | Yes | Auto Scheduled | Phase 2: Establish Guideline Oversight Committee /Explore international Collaboration /External Partners/SMEs | 52.54 days? | July 12, 2021 4:40 PM | September 23, 2021 12:00 PM | 1 | 1
12 | Yes | Auto Scheduled | Phase 3: Establish Workgroups: (Guideline Panel, Informatics, CDS Implementors, Systematic Review Team | 7 days? | July 12, 2021 4:40 PM | July 21, 2021 4:40 PM |  | 2
13 | Yes | Auto Scheduled | Convene an oversight committee/group, determine goals, roles, and responsibilities, and assess conflict of interest. | 1 day? | July 12, 2021 4:40 PM | July 13, 2021 4:40 PM |  | 3
14 | Yes | Auto Scheduled | Establish an evaluation team | 1 day? | July 13, 2021 4:40 PM | July 14, 2021 4:40 PM | 13 | 3
15 | Yes | Auto Scheduled | Establish project management plan, including time frame and milestones, for specific guideline topic. | 1 day? | July 14, 2021 4:40 PM | July 15, 2021 4:40 PM | 14 | 3
16 | Yes | Auto Scheduled | Establish guideline workgroup(s) | 1 day? | July 15, 2021 4:40 PM | July 16, 2021 4:40 PM | 15 | 3
17 | Yes | Auto Scheduled | Identify and establish collaborations and/or partnerships. | 1 day? | July 16, 2021 4:40 PM | July 19, 2021 4:40 PM | 16 | 3
18 | Yes | Auto Scheduled | Conduct kickoff meeting with relevant stakeholders | 1 day? | July 19, 2021 4:40 PM | July 20, 2021 4:40 PM | 17 | 3
19 | Yes | Auto Scheduled | Develop communication plan and estimated timeline of activities to do before, during, and after release of guideline, including a plan for tracking results. | 1 day? | July 20, 2021 4:40 PM | July 21, 2021 4:40 PM | 18 | 3
20 | Yes | Auto Scheduled | Set-up collaborative platforms and tools | 1 day? | July 12, 2021 4:40 PM | July 13, 2021 4:40 PM |  | 3
21 | Yes | Auto Scheduled | Phase 4: Scope Guideline Identify Computable Clinical Practice Guideline (CPG) Concepts | 31.54 days? | July 21, 2021 4:40 PM | September 3, 2021 12:00 PM | 12 | 2
22 | Yes | Auto Scheduled | Phase 4: Scope Guideline Identify Computable Clinical Practice Guideline (CPG) Concepts | 0 days? | July 23, 2021 1:00 PM | July 23, 2021 1:00 PM |  | 3
23 | Yes | Auto Scheduled | Phase 4: Scope Guideline Identify Computable Clinical Practice Guideline (CPG) Concepts | 0 days? | September 3, 2021 12:00 PM | September 3, 2021 12:00 PM |  | 3
24 | Yes | Auto Scheduled | Convene scoping group | 1 day? | July 21, 2021 4:40 PM | July 22, 2021 4:40 PM |  | 3 | The Scope Management Plan defines the degree of rigor to be applied to the project based on it's size, complexity, risk tolerance and organizational importance.
25 | Yes | Auto Scheduled | Get input for the scope of the guideline | 1 day? | July 21, 2021 4:40 PM | July 22, 2021 4:40 PM |  | 3
26 | Yes | Auto Scheduled | Develop draft scope | 1 day? | July 21, 2021 4:40 PM | July 22, 2021 4:40 PM |  | 3
27 | Yes | Auto Scheduled | a.Use preliminary assessments to set guideline objectives, key research questions. Develop PICO to reflect guideline objectives, and which research questions must be answered to arrive at a recommendation. | 1 day? | July 21, 2021 4:40 PM | July 22, 2021 4:40 PM |  | 3
28 | Yes | Auto Scheduled | b.Consider key issues, PICO, and make initial scoping decisions | 1 day? | July 21, 2021 4:40 PM | July 22, 2021 4:40 PM |  | 3
29 | Yes | Auto Scheduled | c.Discuss key research questions and scope with INFO SME, and what information is needed and how to frame it for a computable guideline. | 1 day? | July 21, 2021 4:40 PM | July 22, 2021 4:40 PM |  | 3
30 | Yes | Auto Scheduled | d.Consult with IMPL SME to evaluate plausible clinical workflows impacting scope of intervention and settings | 10 days | July 21, 2021 4:40 PM | August 4, 2021 4:40 PM |  | 3
31 | Yes | Auto Scheduled | Develop a visual analytic model showing a causal pathway for the proposed research questions and intervention(s) in PICO. | 1 day? | July 21, 2021 4:40 PM | July 22, 2021 4:40 PM |  | 3
32 | Yes | Auto Scheduled | Consult with INFO SME to inform and refine scope. | 1 day? | July 21, 2021 4:40 PM | July 22, 2021 4:40 PM |  | 3
33 | Yes | Auto Scheduled | Finalize guideline scope after consultation with the oversight committee and partners | 1 day? | July 21, 2021 4:40 PM | July 22, 2021 4:40 PM |  | 3
34 | Yes | Auto Scheduled | Update draft of communications plan | 1 day? | July 21, 2021 4:40 PM | July 22, 2021 4:40 PM |  | 3
35 | Yes | Auto Scheduled | Draft an evaluation plan for the guideline product, process and outcome, based on logic model | 1 day? | July 21, 2021 4:40 PM | July 22, 2021 4:40 PM |  | 3
36 | Yes | Auto Scheduled | Phase 5 - Identify, Assess, and Synthesize Evidence | 9 days? | September 3, 2021 1:00 PM | September 16, 2021 12:00 PM | 21 | 2 | Identify and assign project resources, determine project activity and task dependencies, develop task estimates develop the project schedule.
37 | Yes | Auto Scheduled | Select evidence review methods and infrastructure most appropriate for the guideline under development | 1 day? | September 3, 2021 1:00 PM | September 6, 2021 12:00 PM |  | 3 | Develop the project structure in terms of detailed phases, activities, tasks, deliverables, and resources.
38 | Yes | Auto Scheduled | Decide how information and evidence regarding critical questions identified in Phase 4 will be addressed. | 1 day? | September 6, 2021 1:00 PM | September 7, 2021 12:00 PM | 37 | 3 | Identify resources (human and other) that will be required to successfully deliver the project
39 | Yes | Auto Scheduled | Identify evidence and extract information. | 1 day? | September 7, 2021 1:00 PM | September 8, 2021 12:00 PM | 38 | 3 | Produce a detailed estimates of the costs and material resources required to deliver each component of the Work Breakdown Structure.
40 | Yes | Auto Scheduled | Assess evidence. | 1 day? | September 8, 2021 1:00 PM | September 9, 2021 12:00 PM | 39 | 3 | Define the milestones and phase dates for each component of the Work Breakdown Structure, and identify the dependencies between the work components (the network logic).
41 | Yes | Auto Scheduled | Synthesize evidence and define a process for writing draft text for manuscript for Phase 7. | 1 day? | September 9, 2021 1:00 PM | September 10, 2021 12:00 PM | 40 | 3
42 | Yes | Auto Scheduled | a.Synthesize published and unpublished evidence into tables/evidence profiles for each key question, including quality of evidence, magnitude of effect, and | 1 day? | September 10, 2021 1:00 PM | September 13, 2021 12:00 PM | 41 | 3
43 | Yes | Auto Scheduled | b.Evaluate and rate the quality of the body of evidence using pre-defined criteria (for each research question). | 1 day? | September 13, 2021 1:00 PM | September 14, 2021 12:00 PM | 42 | 3
44 | Yes | Auto Scheduled | c.Develop a process for drafting text for manuscript through organization's oversight committee for all guidelines. | 1 day? | September 14, 2021 1:00 PM | September 15, 2021 12:00 PM | 43 | 3
45 | Yes | Auto Scheduled | Specify computable CPG artifacts | 1 day? | September 15, 2021 1:00 PM | September 16, 2021 12:00 PM | 44 | 3 | Maintain an ongoing list of the assumptions on which the estimates and schedules are based.
46 | Yes | Auto Scheduled | Phase 6 -Formulate (Craft) the Recommendations | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM | 36 | 2 | Identify, analyze and profile project risks,
47 | Yes | Auto Scheduled | Develop, rate, and prioritize recommendations. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
48 | Yes | Auto Scheduled | a.Review rules (if any) for process for wording of recommendations (e.g., one person followed by comments, group effort, and sentence structure) that is consistent with computable guidelines (e.g. logical, computer interpretable format). | 0.5 days? | September 16, 2021 1:00 PM | September 16, 2021 5:00 PM |  | 3 | Describe the methods and procedures to be used to identify, evaluate, and eliminate or minimize project risks.
49 | Yes | Auto Scheduled | b.Review the evidence and formulate draft recommendation(s). (add a sentence about already published recommendations) | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
50 | Yes | Auto Scheduled | c.Describe information in support of the recommendation(s) (e.g., rationale for group decisions, benefit vs. harm considerations, patient values and preferences) | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
51 | Yes | Auto Scheduled | d.Rate recommendation strength/class of recommendation (e.g., strong, weak) and direction (e.g., for, against) based on quality/Level of evidence. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
52 | Yes | Auto Scheduled | e.Based on pre-determined steps, finalize draft recommendations (e.g., voting of members, public comment) and voting/comment options (e.g., agree/disagree, agree if modified in strength or wording) and timing (relative to entire guideline text). | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
53 | Yes | Auto Scheduled | f.Drawing upon previous rating of each recommendation, prioritize which recommendations are suitable for developing computable CPG using various criteria, e.g., strength of vidence and magnitude of the effect (strong evidence and strong recommendation), | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
54 | Yes | Auto Scheduled | Create case presentation, use cases, user stories for recommendations where clinical decision support is appropriate. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
55 | Yes | Auto Scheduled | a.From patient-centered characteristics, refine and expand clinical decision support design artifacts, use cases & their diagrams, case presentations, user stories. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
56 | Yes | Auto Scheduled | Represent narrative recommendations (as appropriate) into logical diagrams for use in creating computable guideline. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
57 | Yes | Auto Scheduled | a.Based on analysis, translate related/bundled recommendations into algorithmic decision trees, data capture needs, concept maps or decision analyses (if applicable). | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
58 | Yes | Auto Scheduled | b.Create a semi-structured diagram (L2) representing the steps involved in implementing the recommendation at the clinical level. Digram should incorporate previous analyses to model the work, such as decision trees | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
59 | Yes | Auto Scheduled | Conduct mid-progress internal review(s) of Phase 6 and previous phases and computable CPG design meeting with SME’s and relevant stakeholders. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
60 | Yes | Auto Scheduled | a.Guideline developrs present recommendations in development. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
61 | Yes | Auto Scheduled | b.Informaticians and implementors present case presentation, user stories, use cases, use case diagram, decision trees, flowcharts,workflow diagrams, proposed terminology, data elements, and other work products. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
62 | Yes | Auto Scheduled | c.Implementors facilitate feedback on work products from clinicians (end-users) and decision support (EHR/CDS) developers. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
63 | Yes | Auto Scheduled | d.Team members refine their work products based on the review and design work | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
64 | Yes | Auto Scheduled | Design and build computable CPG artifacts as indicated by prioritization activities and available resources, if resources allow. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
65 | Yes | Auto Scheduled | a.Develop CPG expression (L3) building on flow diagrams, decision trees, and other work products. Use standards-based interoperable languages where possible (e.g., CQL, BPM+). | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
66 | Yes | Auto Scheduled | b.Create data elements. Identify existing profiles, value sets, libraries, groups, and rules and those that have parameters; build new elements as needed. Build profiles, value sets, libraries, groups, rules, and logic. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
67 | Yes | Auto Scheduled | c.Identify comprehensive test cases and testing resources (e.g. sandboxes) required to evaluate computable CPG artifacts. Test cases may include case features, recommendations and logic representations based on patient data; may include workflows dependi | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
68 | Yes | Auto Scheduled | Test the computable CPG artifacts | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
69 | Yes | Auto Scheduled | a.Set up test environment to include appropriate patient-level test data. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
70 | Yes | Auto Scheduled | b. Implement test scenarios | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
71 | Yes | Auto Scheduled | c.Verify that the computable guideline performs as expected. Use test cases to assure that the computable artifacts provide outputs consistent with the narrative guidelines. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
72 | Yes | Auto Scheduled | Determine what health information technology (HIT) and informatics resources are needed to support computable CPG implementation. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
73 | Yes | Auto Scheduled | a.Specify the current IT resources and standards needed to retrieve and implement the computable CPG artifacts in a test system. e.g., FHIR release 4, Value Set Authority Center (VSAC) at https://vsac.nlm.nih.gov/." | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
74 | Yes | Auto Scheduled | Phase 7 - Draft the Guideline Finalize computable CPG artifacts; create documentation | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM | 45 | 2
75 | Yes | Auto Scheduled | Review the defined process by which draft text will be written. (Phase 5, activity 5) | 0.5 days? | September 16, 2021 1:00 PM | September 16, 2021 5:00 PM |  | 3 | Establish the baseline against which project quality will be measured and describe the methods and procedures to be used for monitoring and verifying project quality.
76 | Yes | Auto Scheduled | a.Review process for drafting text through organization's oversight committee for all guidelines. Tailor to each guideline based on factors (e.g., guideline type, rapidity). | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
77 | Yes | Auto Scheduled | b.Finalize plan for timeline, roles, & responsibilities. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3 | Determine the following:...
78 | Yes | Auto Scheduled | Set specific expectations regarding the text development process. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
79 | Yes | Auto Scheduled | a.Remind participants of expectations as the writing proceeds. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3 | example:...
80 | Yes | Auto Scheduled | Develop content to supplement recommendations of the guideline | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
81 | Yes | Auto Scheduled | a.As per agreed upon outline and guideline format, include content | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3 | As per agreed upon outline and guideline format, include content: rationale/need for the guideline, guideline scope, methods including literature search strategy, names and affiliations of oversight committee, workgroups, conflict of interest statements,
82 | Yes | Auto Scheduled | Write supporting guideline text (i.e. text other than recommendations) | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
83 | Yes | Auto Scheduled | a.Draft content according to outline and other requirements of journal or other publication venue. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
84 | Yes | Auto Scheduled | b.Begin writing before all recommendations are written. Use an iterative approach to writing, reviewing, and editing for clarity | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
85 | Yes | Auto Scheduled | c.Add any needed supporting citations | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
86 | Yes | Auto Scheduled | Conduct quality assessment of the guideline | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3 | Use an appraisal instrument to conduct quality assessment of guideline to check if it meets established quality standards and reporting criteria
87 | Yes | Auto Scheduled | Finalize computable CPG artifacts (L3) and documentation, to include drafts of user needs, use cases, and other informatics design artifacts. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
88 | Yes | Auto Scheduled | a.Finalize CPG expressions (L3) and definitional knowledge assets (e.g., declarative or models). | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
89 | Yes | Auto Scheduled | b.Validate entire CPG end-to-end. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
90 | Yes | Auto Scheduled | c.Identify expected common derivatives (e.g. eCQM, eCase reports, CDS) desired by guideline development group, other key stakeholder incl end-user/ consumer reps | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
91 | Yes | Auto Scheduled | d.Identify requirements related to making resources findable on digital platforms, (e.g., tagging of specific sections based on content-based terminologies and ontologies.) | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
92 | Yes | Auto Scheduled | e.Develop documentation | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
93 | Yes | Auto Scheduled | Prepare computable CPG artifacts and documentation for online repositories | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
94 | Yes | Auto Scheduled | a.Prepare artifacts to include use cases, use case diagrams, decision trees, flowcharts, workflow diagrams, proposed data elements, and other informatics design artifacts to make available online when the guideline is published | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3 | b. Use an iterative approach with writing/editing, and structuring of text among guideline co-authors, informaticians, and implementors.
95 | Yes | Auto Scheduled | b.Prepare final repositories and libraries for concepts, data elements (profiles, terminologies, value sets, libraries, groups, rules, and logic | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
96 | Yes | Auto Scheduled | c.Finalize and document necessary tags, structured terminology elements, and other content related to informatics requirements associated with guideline text. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
97 | Yes | Auto Scheduled | d.Ensure communications and publication teams are aware of any items that will be published." | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
98 | Yes | Auto Scheduled | Obtain feedback on text and incorporate any necessary edits or copyedits | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
99 | Yes | Auto Scheduled | a.Determine how to obtain and consolidate feedback from co-authors, oversight committee, external SMEs, and organizational authorities | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3 | Use an iterative approach with writing/editing, and structuring of text among guideline co-authors, informaticians, and implementors.
100 | Yes | Auto Scheduled | Obtain approval (if required by policy) to move to next step. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3 | Approach depends on organizational policies, as defined in earlier steps.
101 | Yes | Auto Scheduled | Update evaluation plan for guideline implementation, based on logic model, and develop criteria for updating guideline. (add "outcomes" to "evaluation") | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
102 | Yes | Auto Scheduled | a.Update outcomes evaluation plan based on logic model and address: | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3 | WHAT is the theoretical framework for the evaluation?...
103 | Yes | Auto Scheduled | b.Brainstorm, and prioritize draft evaluation questions and appropriate methods to answer them. Methods can be qualitative, quantitative, mixed methods, naturalistic inquiry, and research design, e.g., pre-post, experimental, time series. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
104 | Yes | Auto Scheduled | c.Choose/develop the evaluation instruments and methods, e.g., surveys, focus groups, or interviews. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
105 | Yes | Auto Scheduled | d.Develop criteria for updating guideline, e.g., a guideline can be updated due to evaluation outcomes or changes in meta-analysis parameter estimates. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
106 | Yes | Auto Scheduled | Ensure COM plan is shared/agreed upon by all relevant parties, and revise COM plan based on other's input | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
107 | Yes | Auto Scheduled | a.Hold meeting to ensure guideline and other leads agree with COM plan. | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3
108 | Yes | Auto Scheduled | b.Coordinate with the organizations’ relevant staff (e.g. communication, media, and policy staff | 1 day? | September 16, 2021 1:00 PM | September 17, 2021 12:00 PM |  | 3 | Coordinate with the organizations’ relevant staff (e.g. communication, media, and policy staff about:...
109 | Yes | Auto Scheduled | Phase 8 - Finalize Manuscript for Internal Review / External Review / Peer Review / and Public Comment | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM | 74 | 2
110 | Yes | Auto Scheduled | Finalize the draft narrative guideline and derivative products for formal review. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
111 | Yes | Auto Scheduled | a.Apply the agreed upon or a standardized format for the guideline, with structure, headings, and content. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3 | Full Guideline Draft
112 | Yes | Auto Scheduled | b.Edit the full draft. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3 | Full Guideline Draft
113 | Yes | Auto Scheduled | c.Finalize draft computable CPG artifacts. Includes all design artifacts, computational assets, and resources allowing event condition action (ECA) rules, metrics. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3 | Derivative products
114 | Yes | Auto Scheduled | d.Finalize draft of other products – quick guides, mobile apps, pocket cards for different audiences (e.g., consumers, providers). Ensure appropriate design, logos, and branding. Pilot test some products, if possible. Determine how to shorten that proces | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3 | Derivative products
115 | Yes | Auto Scheduled | Conduct external review, and revise recommendations and derivative products as needed | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
116 | Yes | Auto Scheduled | a.Decide on the method(s) for engaging external review of the final document(s), including manuscript & derivative products | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3 | • Invited SMEs ...
117 | Yes | Auto Scheduled | b.Incorporate feedback and responses into document and produce next draft. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
118 | Yes | Auto Scheduled | c.Make alterations to the guideline recommendations with the agreement of the guideline workgroup. If needed, revise the CPG recommendations & products. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
119 | Yes | Auto Scheduled | c.Software options (e.g., online review, mobile app reviewer alerts) | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3 | Informatics
120 | Yes | Auto Scheduled | d.Access easily searchable database of multidisciplinary potential reviewers | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3 | Informatics
121 | Yes | Auto Scheduled | Release computable CPG and derivatives (based on narrative guideline) for comment by users | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
122 | Yes | Auto Scheduled | a. Invite additional validation and (remove) feedback by user groups, partner organizations, and industry. (not intended to be used in clinics) by including cross-posted links to the computable content with a link to the narrative guideline draft. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
123 | Yes | Auto Scheduled | Ensure transparency and documentation. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
124 | Yes | Auto Scheduled | a.Document the internal and external peer review process. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
125 | Yes | Auto Scheduled | b.Document the selection and enrollment of consumers and stakeholders. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
126 | Yes | Auto Scheduled | c.If applicable, publish comments and the guideline dev. group responses. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
127 | Yes | Auto Scheduled | Revise and finalize the draft | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
128 | Yes | Auto Scheduled | a.Writer-editor performs final editing. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
129 | Yes | Auto Scheduled | b.Guideline workgroup reviews and signs off. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
130 | Yes | Auto Scheduled | Conduct organizational review of manuscript and approval (if required by organization). | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
131 | Yes | Auto Scheduled | a.Submit the draft and derivative products to organizational clearance mechanism for review and approval | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3 | e.g. federal/HHS - may need Asst. Sec. for Public Affairs (ASPA) clearance
132 | Yes | Auto Scheduled | Ensure all COM products/messages/social media are approved and are easily accessible, and address different audience needs and risks. Revisit stakeholder analysis. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
133 | Yes | Auto Scheduled | a.Ensure products meet audience needs, preferences, and reading level. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
134 | Yes | Auto Scheduled | b.Revisit stakeholder analysis to identify COM channels that will best reach stakeholders | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3 | e.g., mass media vs. specialty channels, health information technology (HIT) and topic domain clinical decision support influencers.
135 | Yes | Auto Scheduled | Assess potential media interest, statements/and outreach. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
136 | Yes | Auto Scheduled | a.Determine if a press release and clearance among contributing organizations is needed. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
137 | Yes | Auto Scheduled | b.Identify partners who are trusted sources to share embargoed COM plan. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
138 | Yes | Auto Scheduled | c.Identify and ensure prep for spokespersons for key messages/webinars, etc | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
139 | Yes | Auto Scheduled | Conduct environmental scan prior to release | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
140 | Yes | Auto Scheduled | a.Prior to release, conduct an environmental scan to assess issues surrounding guidelines. Assess risk communication. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3 | Assess risk communication. For example: is there an outbreak for a specific pathogen related guideline; a new policy from a regulatory agency; or a congressional testimony or new data being released related to guideline?
141 | Yes | Auto Scheduled | b.Plan for controversy, confusion and need for clear communication | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
142 | Yes | Auto Scheduled | c.Archive outdated guideline annually (remove) and replace with updated guideline. For example, AIDS INFO and CHEST guidelines insert a message saying this guideline is the updated version. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
143 | Yes | Auto Scheduled | d.Determine if there are old/outdated guidelines, products, CDS, training material, policies that need to be withdrawn or archived or labeled before or parallel to the release of new guidelines. Be clear about what’s been updated if the guideline is an u | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
144 | Yes | Auto Scheduled | Submit manuscript and other products for publication. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
145 | Yes | Auto Scheduled | a.Send final approved draft and products for publication. | 1 day? | September 17, 2021 1:00 PM | September 20, 2021 12:00 PM |  | 3
146 | Yes | Auto Scheduled | Phase 9: Publish and Disseminate Guideline | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM | 109 | 2
147 | Yes | Auto Scheduled | Ensure all dissemination approaches, platforms, and content are ready to be used, e.g., website, links. | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
148 | Yes | Auto Scheduled | a.Assess and prepare for dissemination strategies on different platforms; develop clear communication detailed timeline for publication & dissemination. | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
149 | Yes | Auto Scheduled | b.Coordinate dissemination modalities with web team(s). | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
150 | Yes | Auto Scheduled | c.Finalize plans for printing, posting in guideline repositories among stakeholders | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3 | e.g., partners, advocates, researchers, etc. Determine which finalized materials will be used, posted on web and digital platforms, e.g., CDS Connect. Determine if visualization is needed to ensure documents are accessible to those with disabilities.
151 | Yes | Auto Scheduled | Coordinate with journal and partners’ communication team | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
152 | Yes | Auto Scheduled | a.Share and coordinate delivery of promotional materials, e.g., seminars, webinars for continuing education, blogs, editorials, implementation guides, fact sheets. | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
153 | Yes | Auto Scheduled | Prep and coordinate with people who will be speaking about the textual and computable guidelines (e.g., author, organizational leaders). | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
154 | Yes | Auto Scheduled | a.Finalize talking points, media statement, FAQs, emails and notifications to partners, and other public-facing messages. | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
155 | Yes | Auto Scheduled | b.Conduct practice sessions to role play and prepare for anticipated questions and responses to the media | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
156 | Yes | Auto Scheduled | Launch communication and timed-release plan when manuscript is published and derivative products are approved for release. | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
157 | Yes | Auto Scheduled | a.Prepare spokespersons, messages, webinars, etc. Ensure dissemination modalities, e.g., key partners, media, are ready for guideline and product distribution | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
158 | Yes | Auto Scheduled | b.Start formal implementation, communication, and dissemination activities, e.g., release guideline and products. | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
159 | Yes | Auto Scheduled | Track results of launched communication plan to determine if a successful release. | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
160 | Yes | Auto Scheduled | a.Track activities and measure success of dissemination using current industry standard techniques and metrics (e.g., number of paid and earned media placements, size of reach to intended audiences, engagement of stakeholders, etc. | 1 day? | September 20, 2021 1:00 PM | September 21, 2021 12:00 PM |  | 3
161 | Yes | Auto Scheduled | Phase 10: Implement Guideline Locally | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM | 146 | 2
162 | Yes | Auto Scheduled | Prioritize, select, and promote guideline recommendations to implement. | 0.5 days? | September 21, 2021 1:00 PM | September 21, 2021 5:00 PM |  | 3
163 | Yes | Auto Scheduled | a.Conduct care gap analysis between guideline recommendation and local practice, if possible. Assess potential beneficial impact at the local level. (optional) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
164 | Yes | Auto Scheduled | b.Conduct local feasibility assessment (- what stakeholders are impacted and how guidelines fit and are harmonized with existing information systems, such as CDS workflow & requirements). (optional) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
165 | Yes | Auto Scheduled | c.Make decision which guidelines/CDS to implement. Provide analysis to the implementation team to inform project. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
166 | Yes | Auto Scheduled | d.Develop project scope statement and evaluation strategy, including baseline assessment, and implementation and evaluation strategy. (may be informal) (add Duwayne’s reference) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
167 | Yes | Auto Scheduled | e.Communicate decision to implement. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
168 | Yes | Auto Scheduled | Analyze local workflow and context | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
169 | Yes | Auto Scheduled | a.Assess current local workflow including degree of provider burden associated with the proposed CDS. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
170 | Yes | Auto Scheduled | b.Engage stakeholders about proposed CDS implementation. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
171 | Yes | Auto Scheduled | Conduct feasibility assessment (Technical) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
172 | Yes | Auto Scheduled | a.Assess feasibility of implementing the CDS within local clinical information systems, e.g., HER, lab systems, pharmacy systems in terms of structured data, CDS triggers, and actions envisioned | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
173 | Yes | Auto Scheduled | b.Assess feasibility for measuring the effectiveness of CDS using local EHR and analytic capabilities. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
174 | Yes | Auto Scheduled | Design local clinical implementation. (e.g., Localization of new workflow, any L3 to L4 adjustments) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
175 | Yes | Auto Scheduled | a.Map workflow, including end user perspectives. Use real-world recent use cases to validate designs; locate records/data that inform these use cases. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
176 | Yes | Auto Scheduled | b.Design IT artifacts/features within local system architecture. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
177 | Yes | Auto Scheduled | c.Formalize an approach to measuring impact and outcomes, including metrics that can improve clinical practice and patient care. (optional) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
178 | Yes | Auto Scheduled | d.Determine how data needed for measurement will be captured locally from HER and other sources e.g., define what population and other conditions are in denominator. (optional) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
179 | Yes | Auto Scheduled | e.Start to develop training (localize) and make clinicians aware of any workflow changes. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
180 | Yes | Auto Scheduled | f.If needed, repeat above for multiple EHRs in the local environment. (optional) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
181 | Yes | Auto Scheduled | Mid-progress review and launch planning | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
182 | Yes | Auto Scheduled | a.Review design before build and testing. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
183 | Yes | Auto Scheduled | b.Plan launch, e.g. go-live staffing (optional) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
184 | Yes | Auto Scheduled | Build and test L4 artifacts and features in EMR. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
185 | Yes | Auto Scheduled | a.Build and unit test L4 artifacts/features using real-world use cases | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3 | example: Value sets, logic records, rules...
186 | Yes | Auto Scheduled | b.Consider synthetic testing with sandboxes using simulated patients or EHRs, if available. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
187 | Yes | Auto Scheduled | c.Conduct a build review. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
188 | Yes | Auto Scheduled | d.Demo to clinical stakeholders and build consensus among practitioners. (optional) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
189 | Yes | Auto Scheduled | Test clinical information systems and decision support | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
190 | Yes | Auto Scheduled | a.Write localized test scripts and conduct integrated system testing. Use real-world recent use cases & records/data to test systems. Test local system and connectivity to outside resources (e.g. APIs). | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
191 | Yes | Auto Scheduled | b.Conduct clinical validation through user acceptance testing, workflow validation, and usability testing, if appropriate. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3 | For example: Test with real patients, non-visible to clinicians; test in production by small number of clinicians; pilot in a small subset of clinical settings and provide feedback.
192 | Yes | Auto Scheduled | c.Revise clinical information systems and decision support as needed, based on testing and user feedback. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
193 | Yes | Auto Scheduled | Update policy & procedures, as needed; educate and train end users how to use guidelines in clinical decision support, using the most appropriate methods. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
194 | Yes | Auto Scheduled | a.Update organizational policies and procedures, as needed. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
195 | Yes | Auto Scheduled | b.Update education with local systems final interface design, i.e., screenshots | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
196 | Yes | Auto Scheduled | c.Decide who to train, & how to best deliver training; tailor to local training channels | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
197 | Yes | Auto Scheduled | d.Train end users on how to use guidelines in clinical decision support. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
198 | Yes | Auto Scheduled | Deploy clinical guidelines artifact(s) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
199 | Yes | Auto Scheduled | a.Determine date to deploy new clinical decision support, based on operational readiness. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
200 | Yes | Auto Scheduled | b.Update and execute go-live staffing plan for release of clinical decision support for clinicians | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
201 | Yes | Auto Scheduled | c.Migrate artifacts from development to testing to production | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
202 | Yes | Auto Scheduled | d.Test with real patients, non-visible to clinicians. (silently). (optional | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
203 | Yes | Auto Scheduled | e.Test in production by small number of clinicians (optional) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
204 | Yes | Auto Scheduled | f.Pilot in a small subset of clinical settings and provide feedback. (optional) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
205 | Yes | Auto Scheduled | Use clinical decision support artifact(s) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
206 | Yes | Auto Scheduled | a.Use system as designed. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
207 | Yes | Auto Scheduled | b.Assess end user interactions with clinical decision support, e.g., observations or data on usage patterns. Identify variations across users. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
208 | Yes | Auto Scheduled | c.Users provide feedback (subjective and real time). Assist users as needed | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
209 | Yes | Auto Scheduled | Assess and refine the CDS tools. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
210 | Yes | Auto Scheduled | a.Conduct quantitative assessment per measurement strategy. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
211 | Yes | Auto Scheduled | b.Conduct qualitative assessment e.g., focus groups; build satisfaction surveys into artifacts. (optional) | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
212 | Yes | Auto Scheduled | c.Report findings to leadership and quality improvement group | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
213 | Yes | Auto Scheduled | d.Optimize CPG artifacts, including CDS tools and update local documentation accordingly. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
214 | Yes | Auto Scheduled | e. Repeat the assessment of the refined CDS tools | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
215 | Yes | Auto Scheduled | Provide feedback to guideline developer and implementor on the computable CPG. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
216 | Yes | Auto Scheduled | a.Report feedback from end-users and other relevant data sources. | 1 day? | September 21, 2021 1:00 PM | September 22, 2021 12:00 PM |  | 3
217 | Yes | Auto Scheduled | Phase 11: Evaluate Guideline Outcomes and Impact | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM | 161 | 2
218 | Yes | Auto Scheduled | Tailor and finalize guideline evaluation plan and questions to context of local implementation, such as a regional health care system, hospital network, or individual clinics. | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
219 | Yes | Auto Scheduled | a.Finalize evaluation questions. Guideline implementation evaluation is dependent on program and stakeholder priorities and feasibility of conducting the evaluation per resources. The plan should be flexible and adaptive | 0.5 days? | September 22, 2021 1:00 PM | September 22, 2021 5:00 PM |  | 3
220 | Yes | Auto Scheduled | b.Adapt and finalize methods for collecting, analyzing, and sharing data/findings via feedback loops to the guideline developers | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
221 | Yes | Auto Scheduled | c.Reconsider environmental context | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
222 | Yes | Auto Scheduled | Implement the evaluation plan at the time the guideline is released, and in conjunction with the communication plan. | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
223 | Yes | Auto Scheduled | a.Launch evaluation plan | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
224 | Yes | Auto Scheduled | b.Collect, summarize, and document the first wave of results, e.g., hits on the narrative document; downloads of CDS code, unsolicited user feedback. Evaluation iimplementation process issues, awareness and knowledge improvements, if feasible, (short-te | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
225 | Yes | Auto Scheduled | c.Present results to guideline authors, oversight committee, and partners | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
226 | Yes | Auto Scheduled | d.Collect, summarize, and document the second wave of results, e.g., behavioral and policy changes, if feasible (intermediate evaluation). | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
227 | Yes | Auto Scheduled | e.Present results to guideline authors, oversight committee and partners | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
228 | Yes | Auto Scheduled | f.Collect, summarize, and document the third wave of results, e.g., health outcome improvements, if feasible (distal evaluation). | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
229 | Yes | Auto Scheduled | g.Present results to guideline authors, oversight committee, and partners. | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
230 | Yes | Auto Scheduled | h.Submit feedback and suggestions for guideline update for phase 12 – guideline update, based on results, new evidence, other criteria, e.g., a guideline can be updated because of evaluation outcomes or changing parameter estimates. | 1 day? | September 22, 2021 1:00 PM | September 23, 2021 12:00 PM |  | 3
231 | Yes | Auto Scheduled | Phase 12: Update Guideline | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM | 11 | 1
232 | Yes | Auto Scheduled | Create management or operational plan for updating the narrative and computable guidelines. Determine if a major or minor update is needed | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
233 | Yes | Auto Scheduled | a.Refine criteria for updating guidelines (who, what, when-time frame, how) including the types of updates and their scope. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
234 | Yes | Auto Scheduled | b.Determine the methods, scope, type of updates, and prioritization needed to update the quality of evidence for a specific recommendation(s) in a guideline. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
235 | Yes | Auto Scheduled | c.Define and establish resources to create a system that supports continuous and timely feedback and updating of the narrative and computable guideline, according to established criteria. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2 | Sub-steps include detailing project management plans, staffing and reporting structure, infrastructure required (cloud computing) software procurement, and associated costs, etc.).
236 | Yes | Auto Scheduled | Use on-line resources, e.g., standardized registries and repositories to hold, share, and receive feedback on guideline data, content, and digitized components. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
237 | Yes | Auto Scheduled | a.Create electronic (on-line) and other feedback mechanisms. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
238 | Yes | Auto Scheduled | b.Develop specifications to create, manage, and maintain documentation of technical and informatics knowledge associated with the guideline. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
239 | Yes | Auto Scheduled | Update systematic reviews as needed to keep them current and relevant. Consider living systematic reviews | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
240 | Yes | Auto Scheduled | a.Review time frame on how frequently new evidence is sought and screened. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
241 | Yes | Auto Scheduled | b.Continuous expert/surveillance teams (example, living systematic review (LSR) Team and guideline sub-workgroup) connected to each knowledge/information byte (recommendation or research question) conduct continual, active monitoring of the evidence (i.e | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
242 | Yes | Auto Scheduled | c.Update systematic review with new evidence. Consider whether PICO questions should be added or revised | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
243 | Yes | Auto Scheduled | d.Where applicable, and if feasible, explore the use of new technologies which utilize human and machine effort, such as artificial intelligence (AI), text mining, machine learning, and crowd sourcing. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
244 | Yes | Auto Scheduled | Update guideline recommendation(s) if needed according to the criteria established in the operational plan for updating recommendations. (see step 1/Task 234) | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
245 | Yes | Auto Scheduled | a.Periodically review feedback, literature evidence, and evaluation results against the criteria in the operational plan to determine whether to update recommendations. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
246 | Yes | Auto Scheduled | b.Develop process to reaffirm recommendation(s) that are not updated. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
247 | Yes | Auto Scheduled | c.Label, remove, replace or archive all outdated guideline recommendation(s) and narrative derivative products. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
248 | Yes | Auto Scheduled | Update related CDS tools as needed based on updated recommendations. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
249 | Yes | Auto Scheduled | a.Review updated recommendations and any other factors, such as local clinical systems feedback, other new evidence that may affect CPG artifacts e.g., changes to value sets or terminologies, software updates for CDS, eCQMs. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
250 | Yes | Auto Scheduled | b.Update CPG artifacts and associated code repositories, systems, policies, and training, as needed. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
251 | Yes | Auto Scheduled | c.Label, remove, replace or archive all outdated CPG artifacts. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
252 | Yes | Auto Scheduled | Monitor the landscape for changes such as new drugs, coding schemes, adverse events that would require modification of L2-L4 and/or CDS. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
253 | Yes | Auto Scheduled | a.Describe the items that need to be monitored, e.g., FDA requirements, new drugs and therapies, adverse events, SNOMED, generic changes in coding schema, e.g., ICD, CPT. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
254 | Yes | Auto Scheduled | Communicate updated recommendations and CDS tools. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
255 | Yes | Auto Scheduled | a.Develop communication and dissemination strategy, tactics, and materials to clearly communicate updated recommendation(s) and derivative products | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
256 | Yes | Auto Scheduled | b.Communicate updated recommendations and derivative products to stakeholders. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2
257 | Yes | Auto Scheduled | c.Evaluate if communication products were used, usable, & useful to users. | 1 day? | September 23, 2021 1:00 PM | September 24, 2021 12:00 PM |  | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Project Manager | P | Work |  |  |  |  | 100% | $0.00/h | 0 | Responsible for management of the project at a strategic level.
2 | Guideline Developer | G | Work |  |  |  |  | 100% | $0.00/h | 0 | Responsible for the delivery of a quality project on-schedule, within budget, with a satisfied Acceptor and a motivated project team.
3 | Informatics- Knwoledge Engineer | I | Work |  |  |  |  | 100% | $0.00/h | 0 | Key individual within the business organization who is the principal interface with the project team and who has the authority to accept all deliverables and resolve all project issues (sometimes referred to as the Project Sponsor).
4 | Informatics- SME | I | Work |  |  |  |  | 100% | $0.00/h | 0 | Defines the major application systems needed to support the enterprise. During systems development, the Application Architect defines the application solution.
5 | Informatics- Terminologist | I | Work |  |  |  |  | 100% | $0.00/h | 0 | Defines the technologies and standards required to support the application and information architectures. During systems development, the Technical Architect defines the technical solution.
6 | Informatics- Software Architect | I | Work |  |  |  |  | 100% | $0.00/h | 0 | Responsible for providing confidence to management that the Quality System is being applied.
7 | Evaluators | E | Work |  |  |  |  | 100% | $0.00/h | 0 | Responsible for managing the contractual interfaces with the customer and with subcontractors.
8 | Communicators | C | Work |  |  |  |  | 100% | $0.00/h | 0
9 | Implementors | I | Work |  |  |  |  | 100% | $0.00/h | 0
10 | jones - coomunicator | j | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Identify functional and operational (including informatics and IT) needs and requirements and limitations for developing narrative and computable guidelines in the organization. | Project Manager | 0 | 1h | 100%
Identify functional and operational (including informatics and IT) needs and requirements and limitations for developing narrative and computable guidelines in the organization. | Communicators | 0 | 1h | 100%
Identify functional and operational (including informatics and IT) needs and requirements and limitations for developing narrative and computable guidelines in the organization. | Evaluators | 0 | 1h | 100%
Identify functional and operational (including informatics and IT) needs and requirements and limitations for developing narrative and computable guidelines in the organization. | Guideline Developer | 0 | 1h | 100%
Identify functional and operational (including informatics and IT) needs and requirements and limitations for developing narrative and computable guidelines in the organization. | Informatics- Knwoledge Engineer | 0 | 1h | 100%
Identify functional and operational (including informatics and IT) needs and requirements and limitations for developing narrative and computable guidelines in the organization. | Informatics- SME | 0 | 1h | 100%
Identify functional and operational (including informatics and IT) needs and requirements and limitations for developing narrative and computable guidelines in the organization. | Informatics- Software Architect | 0 | 1h | 100%
Identify functional and operational (including informatics and IT) needs and requirements and limitations for developing narrative and computable guidelines in the organization. | Informatics- Terminologist | 0 | 1h | 100%
Assess current resources and capacity for guideline development in the organization | Project Manager | 0 | 8h | 100%
Develop an organizational framework for developing a narrative or computable guideline | Guideline Developer | 0 | 8h | 100%
Identify and assess clinical need to identify guideline topic(s) and define clinical questions for a new or updated guideline. | jones - coomunicator | 0 | 8h | 100%
Prioritize topic(s) (if there are more than one proposed topics). | Informatics- SME | 0 | 2h | 100%
Prioritize topic(s) (if there are more than one proposed topics). | Informatics- Terminologist | 0 | 2h | 100%
Prioritize topic(s) (if there are more than one proposed topics). | Guideline Developer | 0 | 4h | 100%
Assess topic and research questions (guideline objective), and communication, informatics, implementation, and evaluation needs. Decide whether to produce a computable version of guideline. | Guideline Developer | 0 | 2.67h | 100%
Assess topic and research questions (guideline objective), and communication, informatics, implementation, and evaluation needs. Decide whether to produce a computable version of guideline. | Informatics- SME | 0 | 2.67h | 100%
Assess topic and research questions (guideline objective), and communication, informatics, implementation, and evaluation needs. Decide whether to produce a computable version of guideline. | Project Manager | 0 | 2.67h | 100%
Obtain leadership approval of topic and funding | Guideline Developer | 0 | 8h | 100%
Convene an oversight committee/group, determine goals, roles, and responsibilities, and assess conflict of interest. | Guideline Developer | 0 | 8h | 100%
Establish an evaluation team | Informatics- Software Architect | 0 | 8h | 100%
Establish project management plan, including time frame and milestones, for specific guideline topic. | Guideline Developer | 0 | 8h | 100%
Develop communication plan and estimated timeline of activities to do before, during, and after release of guideline, including a plan for tracking results. | Guideline Developer | 0 | 8h | 100%
Convene scoping group | Guideline Developer | 0 | 8h | 100%
Select evidence review methods and infrastructure most appropriate for the guideline under development | Guideline Developer | 0 | 8h | 100%
Decide how information and evidence regarding critical questions identified in Phase 4 will be addressed. | Guideline Developer | 0 | 8h | 100%
Identify evidence and extract information. | Guideline Developer | 0 | 8h | 100%
Assess evidence. | Guideline Developer | 0 | 8h | 100%
Specify computable CPG artifacts | Guideline Developer | 0 | 8h | 100%
a.Review rules (if any) for process for wording of recommendations (e.g., one person followed by comments, group effort, and sentence structure) that is consistent with computable guidelines (e.g. logical, computer interpretable format). | Guideline Developer | 0 | 4h | 100%
a.Review rules (if any) for process for wording of recommendations (e.g., one person followed by comments, group effort, and sentence structure) that is consistent with computable guidelines (e.g. logical, computer interpretable format). | Informatics- Knwoledge Engineer | 0 | 4h | 100%
Review the defined process by which draft text will be written. (Phase 5, activity 5) | Informatics- Software Architect | 0 | 4h | 100%
Review the defined process by which draft text will be written. (Phase 5, activity 5) | Informatics- Knwoledge Engineer | 0 | 4h | 100%
a.Apply the agreed upon or a standardized format for the guideline, with structure, headings, and content. | Project Manager | 0 | 8h | 100%
Ensure all dissemination approaches, platforms, and content are ready to be used, e.g., website, links. | Evaluators | 0 | 8h | 100%
c.Finalize plans for printing, posting in guideline repositories among stakeholders | Evaluators | 0 | 8h | 100%
Prioritize, select, and promote guideline recommendations to implement. | Guideline Developer | 0 | 4h | 100%
Prioritize, select, and promote guideline recommendations to implement. | Informatics- Knwoledge Engineer | 0 | 4h | 100%
a.Finalize evaluation questions. Guideline implementation evaluation is dependent on program and stakeholder priorities and feasibility of conducting the evaluation per resources. The plan should be flexible and adaptive | Guideline Developer | 0 | 4h | 100%
a.Finalize evaluation questions. Guideline implementation evaluation is dependent on program and stakeholder priorities and feasibility of conducting the evaluation per resources. The plan should be flexible and adaptive | Informatics- Knwoledge Engineer | 0 | 4h | 100%