Supplementary information

Comparing the performance of year-round and campaign-mode influenza vaccination strategies among children aged 6-23 months in Kenya: 2019 – 2021

Jeanette Dawa, Rose Jalang’o, Harriet Mirieri, Rosalia Kalani, Doris Marwanga, Kathryn E. Lafond, Mary Margaret Njenga, Joyce Ejoi, Faith Chiguba, Shem Patta, Patrick Amoth, Emmanuel Okunga, Collins Tabu, Sandra S. Chaves, Malembe S. Ebama, Philip Muthoka, Virginia Njenga, Elizabeth Kiptoo, Isaac Jewa, Raphael Mwanyamawi, Joseph Bresee, M Kariuki Njenga, Eric Osoro, Lucy Mecca, Gideon O. Emukule

- Preparation for the demonstration project

Prior to  implementation of the influenza vaccine demonstration project, national planning meetings were held to introduce the project, develop the work plan and training materials, and review data collection tools. Thereafter, county and sub-county planning meetings were held with the respective county health management teams (CHMTs) and sub-county health management teams (SCHMTs).

Information education and communication (IEC) materials including posters, roll-up banners, street banners, T-shirts, caps and frequently asked questions (FAQs) were developed in English and Swahili. These were pre-tested among caregivers/parents, community members and healthcare workers before being finalized and distributed. Stakeholder sensitization meetings were held at the sub-county level to inform community gate keepers, opinion leaders, religious leaders, the local government administration and community health volunteers (CHVs) about the project.

At the start of vaccination in each sub-county, the county and sub-county health promotion officers traversed the sub-counties with megaphones on county/sub-county vehicles sensitizing the community about the vaccine. In the campaign strategy sub-counties, social mobilization activities were more intensive. To improve vaccine uptake, especially in Likoni sub county, CHVs were provided monetary reimbursement from mid-way through the campaign strategy.

Immediately prior to implementation of the influenza vaccine demonstration project, trainings were conducted at the national, county and sub-county levels. In addition, 1-2 health care workers (HCWs) at each of the immunizing health facilities in the target sub-counties were trained. Training content included: rationale of the project, vaccine attributes and storage conditions, medical waste management, data management and documentation, advocacy, communication and social mobilization, cold-chain management, and Adverse Event Following Immunization (AEFI) management and reporting.

For the sub-counties implementing the campaign strategy between 10-15 nurses were hired per sub-county to assist with the increased workload expected of the demonstration project. The nurses were stationed at high volume public health  facilities within the sub-county.

Supplementary table 1: ummary of social mobilisation activities per sub county

| Strategy | County | Sub county | Social mobilization activities |
| --- | --- | --- | --- |
| Year round | Nakuru | Njoro | - Sensitisation of sub-county stakeholders - Sensitisation of approximately 180 CHVs each year - Megaphone on a vehicle (1 week) during launch - IEC material – posters, banners, FAQs |
|  | Mombasa | Jomvu | - Sensitisation of sub county stakeholders - Sensitisation of approximately 170 CHVs each year - Megaphone on a vehicle (1 week) during launch - IEC material – posters, banners, FAQs |
| Campaign | Nakuru | Nakuru North | - Sensitisation of sub county stakeholders - Sensitisation of 193 CHVs - Mini-launch - Megaphone vehicle for 1 week (3 times during the campaign) - IEC material – posters, banners, FAQs, T-shirts - CHV reimbursement (50 Kshs) for referral of a child who had defaulted dose 2 (provided in month 4 of 4) |
|  | Mombasa | Likoni | - Sensitisation of sub county stakeholders - Sensitisation of 505 CHVs - Mini-launch - Megaphone vehicle for 1 week at launch - 5 CHVs circulating messages within the community using megaphone for 1 week (4 times during the campaign) - Messages at ferry (beginning month 2 of 4) - IEC material – posters, banners, FAQs, T-shirts - CHV reimbursement (50 Kshs) for every child referred for dose 1 (month 3 of 4) and a child who had defaulted dose 2 (month 4 of 4) |

Kshs – Kenya shillings. Kshs 50 is equivalent to USD 0.46 at an exchange rate of 1 USD = Kshs 107.85

- Estimating target population

We used projections from the National Vaccines and Immunization Program (NVIP). NVIP provides yearly projections of the number of children 0-11 months and 12-59 to be vaccinated in each sub-county. To obtain the number of children 6-23 months of age, we assumed a uniform distribution of children 0-11 months to calculate those aged 6-11 months. To obtain the number of children 12-23 months of age, we used the age distribution of children 1-5 years of age from the 2019 national census to determine that, depending on the sub-county, children 12-23 months of age accounted for 24-27% of children 12-59 months of age (1).

To establish the target population in the campaign strategy and the first year of the year-round strategy, we dealt with children six months of age and 7-23 months of age differently. All children 7-23 months of age formed part of the target population. However, for children aged six months, we bore in mind that over a year, a cohort of children turned six months of age each month and should be included in the target population. If influenza vaccines were offered throughout the year, all children turning six months of age during the year would be vaccinated. However, if the vaccine were provided for a short period (as in the case of a campaign), only a proportion of children that turned six months in that year, proportional to the duration of time within the year vaccination was available, would be eligible for vaccination. Assuming a uniform distribution of children 0-11 months, we obtained the number of children six months of age. We multiplied the figure by 12 to get the total number of children six months of age over a year. We applied a proportion to the yearly number of children aged six months based on the duration the demonstration project was running within that calendar year.

Lastly, we also considered annual population growth and that the start date of vaccination did not align with the NVIP annual target population. We, therefore, obtained the demonstration project target population for a period by applying a proportion to the NVIP annual target population of 2019, 2020, and 2021 based on the number of days the demonstration project was running within that calendar year.

- Additional results of the demonstration project

Public health facilities accounted for the majority of health facilities in the sub-counties implementing the year-round strategy. However, regardless of strategy or sub-county, public health facilities administered most of the vaccines in each sub-county (Supplementary Figure 1).

Supplementary figure 1: Number of heealth facilities per sub-county and number of vaccines administered by health facility type per sub-county in the influenza vaccine demonstration project in Kenya, 2019-2021

Results of each vaccination strategy in each sub-county are provided in Supplementary Table 1 below. We present the results of the first year of the demonstration project in Njoro sub-county (Nakuru county) and Jomvu sub-county (Mombasa county) which implemented the year-round strategy from November/December 2019 to November/December 2020 and the results of the Nakuru North sub-county (Nakuru county) and Likoni sub county (Mombasa county) which implemented the campaign strategy from June/July 2021 to September/October 2021. The summary findings of each strategy are also presented.

Supplementary table 2: Indicators of performance of influenza vaccine demonstration project per sub-county and vaccination strategy in Nakuru and Mombasa counties in Kenya (2019 – 2021)

| Indicator | Year round strategy |  | Campaign strategy |  | Year round strategy | Campaign strategy |
| --- | --- | --- | --- | --- | --- | --- |
|  | Jomvu | Njoro | Likoni | Nakuru North |  |  |
| Target population | 11262 | 16972 | 12060 | 9505 | 28234 | 21565 |
| Day first vaccine dose administered | 16-Dec-19 | 26-Nov-19 | 09-Jul-21 | 02-Jun-21 | 26-Nov-19 | 02-Jun-21 |
| Day last vaccine dose administered | 15-Dec-20 | 25-Nov-20 | 31-Oct-21 | 30-Sep-21 | 15-Dec-20 | 31-Oct-21 |
| Duration of the demonstration exercise | 365 | 365 | 114 | 120 | 385 | 151 |
| Vaccine formulation administered | SH or NH | SH or NH | SH | SH | SH or NH | SH |
| Number of influenza vaccine dose 1 administered | 7227 | 10290 | 6763 | 7341 | 17517 | 14104 |
| Number of influenza vaccine dose 2 administered | 5509 | 7371 | 4954 | 6346 | 12880 | 11300 |
| Coverage dose 1 | 63.1% | 57.4% | 55.2% | 73.4% | 59.7% | 63.2% |
| Coverage dose 2 | 48.1% | 41.1% | 40.4% | 63.5% | 43.9% | 50.6% |
| Dropout rate | 23.8% | 28.4% | 26.7% | 13.6% | 26.5% | 19.9% |
| Wastage | 1.0% | 3.2% | 0.8% | 0.3% | 0.6% | 2.3% |
| Number of AEFIs recorded | 1 | 1 | 2 | 2 | 2 | 4 |
| AEFIs per 100,000 vaccine doses administered | 7.9 (0.4-50.0) | 5.7 (0.3-36.8) | 17.1 (3.0-68.8) | 14.6 (2.5-58.9) | 6.6 (1.1-26.5) | 15.7 (5.0-43.2) |
| Males receiving the first dose of influenza vaccine (%)# | 3726 (51.6%) | 5037 (49.0%) | 3390 (50.1%) | 3642 (49.6%) | 8763 (50.0%) | 7032 (49.9%) |
| Females receiving the first dose of influenza vaccine (%)# | 3459 (47.9%) | 4856 (47.2%) | 3254 (48.1%) | 3592 (48.9%) | 8315 (47.5%) | 6846 (48.5%) |
| Median age in months of children receiving the first dose of influenza vaccine (IQR) | 9.5 (6.9-15.3) | 9.7 (6.9-15.9) | 12.6 (8.9-18.0) | 13.1 (8.9-18.0) | 9.6 (6.9-15.7) | 12.9 (8.9-17.7) |
| Number (%) of children who received the first dose of influenza vaccine at <6 months of age | 207 2.9% | 504 4.9% | 276 4.1% | 257 3.5% | 716 4.1% | 533 3.8% |
| Number (%) of children who received the first dose of influenza vaccine at ≥24 months of age | 10 0.1% | 45 0.4% | 23 0.34% | 34 0.5% | 55 0.3% | 57 0.4% |
| Number of vaccine dose 1 administered to children from target sub-county (%) | 7103 98.3% | 9742 94.7% | 6656 98.4% | 6977 95.0% | 16849 96.2% | 13633 96.7% |
| Number of vaccines administered per day | 35 | 48 | 103 | 114 | 83 | 168 |
| Number of children receiving Vitamin A or other vaccines when receiving the first dose of influenza vaccine (%)# | 3002 (41.5%) | 4987 (48.5%) | 2454 (36.3%) | 2395 (32.6%) | 7989 (45.6%) | 4849 (34.4%) |
| Number of dose 1 records with a linked dose 2 entry (%) | 4178 (57.8%) | 4265 (41.4%) | 3500 (51.8%) | 4879 (66.5%) | 8443 (48.2%) | 8379 (59.4%) |
| Number of children who received dose 1 and dose 2 in the same facility (%) | 3859 (92.4%) | 3934 (92.2%) | 3246 (92.7%) | 4687 (96.1%) | 7793 (92.3%) | 7933 (94.7%) |
| Median duration in days between dose 1 and dose 2 among children with linked dose 1 and 2 records (IQR) | 32 (29-38) | 35 (29-72) | 31 (29-35) | 30 (28-33) | 33 (29-50) | 31 (28-34) |
| Minimum and maximum duration in days between dose 1 and dose 2 among children with linked dose 1 and 2 records | 1-272 | 1-698 | 1-110 | 2-117 | 1-698 | 1-117 |
| Median number of times a facility received influenza vaccine supplies in a month (IQR) | 1 (0-2) | 1 (1-1) | 2 (1.25-4) | 3 (1-4) | 1 (1-1) | 3 (1-4) |

# Data on these variables were unavailable in upto 3% of entries. SH – Southern Hemisphere, NH – Northern Hemisphere

REFERENCES

1. 	2019 Kenya Population and Housing Census Volume III: Distribution of Population by Age, Sex and Administrative Units - Kenya National Bureau of Statistics [Internet]. [cited 2022 Aug 5]. Available from: https://www.knbs.or.ke/?wpdmpro=2019-kenya-population-and-housing-census-volume-iii-distribution-of-population-by-age-sex-and-administrative-units