Additional file 1.  Planned timetable for EQUIP continuous survey teams in Tanzania and Uganda*

| Round number | Survey period (4 months of data collection) | Rest and dissemination | Preparation for next survey period |
| --- | --- | --- | --- |
| 1 | 1 Nov11 – 28 Feb12 | 1-22 Mar12 | 23-31 Mar12 |
| 2 | 1 Apr12 – 31st July12 | 1-22 August12 | 23-31 August12 |
| 3 | 1 Sep12 – 31st Dec12 | 1-22 Feb13 | 23-28 Feb13 |
| 4 | 1Mar-30th Jun13 | 1-22 Jul13 | 23-31 Jul13 |
| 5 | 1Aug-30th Nov13 | 1-27Dec13 | 28-31 Dec13 |
| 6 | 1Jan-31st Apr 14 | END OF SURVEY |  |

*Real dates adapted to allow for country specific events, including public holidays